## Sheet1
Issue/Problem |  |  |  | Likely Root Cause |  |  | Possible Solutions
Decription | Source | Criticality |  | Description | Likelihood (H/M/L) | Info/Tests to Clarify | Description | Risks |  |  | Measure of Success
|  | Level (H/M/L) | Rationale |  |  |  |  | Description | Likelihood | Mitigation | Test | Results
Client is not aware of project status | Client | Medium | Doesn't affect delivery but damaging to account | Status reports not being issued weekly becuz of lack of info from PM | High | Check with office/supervisor to ensure they are aware | Simplify info required for report so it is less time consuming | Client feels reports lack detail | Medium | Agree - detail level could be less for client report | Check with client after 4 weeks | TBA